## Bid Tasking
	Overall Coordinator: Biju Lakshmanan

SECTION	Key Subsections	Leader	Contributors	Deliverables	Deliverable Type	Week 1: 24 to 30 August	Week 2: 31 Aug to 6 Sep	Week 3: 7 to 13 Sep	Week 4: 14 to 20 Sep
DESIGN/ENGINEERING	Design Verification Structures (including utility asset shells)	Ehab	Ehab/Lura	Quantities of: Concrete, Rebar, Structural Steel,Finishes,MEP	BOQ
	Design Verification Infrastructure	Eduardo Lura	Tech Dept MEP	Quantities of: Utility Networks/Manhole chambers/auxiliary structures/Utility assets	BOQ
	Architecture/MEP Check	To be assigned by Ian		Sense check to ensure everything is in place	Exception List
	Ground Stabilization Strategy	Ian	TBA	Method definition. Per method: quantification, accessibility productivity,resource definition	BOQ, resource analysis, areal plan (if possible)
	Temporary Drainage Strategy	To be assigned by Ian		Flood control During Construction: Quantification of elements/Layout	BOQ,plan
METHODS	Quantification of Bulk Earthworks	Senthil	Siva	Earthwork Quantities for roads/utilities/earth walls	BOQ
	Assessment of Excavatability	Jesus/Nikos		Assessment of quantum for breaking,blasting, excavation	BOQ
	Definition of logistics assets	Senthil	Jesus	Definition of areal extent,location and accessibility: laydown areas, crusher yard, concrete plant.	Plans
	Welfare Logistics	Biju	Senthil,Jesus,Moncef	Assessment of transportation logistics from NEOM camps	Report
	Material Transportation Logistics	Senthil	Jesus,Siva	Assessment of main material transportation logistics in terms of road capacity. Internal circulation and access from military road	Plan/Report
	Temporary power and water strategy	Biju	Senthil,Jesus	Definition of supply chain (origin,conveyance,quantum) for: potable water,construction water,diesel,electricity,drainage	Plan/Report
	Earthworks Strategy	Nikos	Senthil/Jesus	Productivity assessment, crushing cycle	Equipment Utilization List
	Concrete Supply Strategy	Biju	Thomas, Nikos, Jesus	Assessment of options and ranking: Existing BPL, Agreement with supplier to install for non exclusive use, own plant. Sourcing of aggregates	Option selection		Integrated Group
	Construction Sequence non hotel	Senthil	Jesus,Siva,Moncef	Integrated construction sequence for chalets,infrastructure,roads,stabilization process.	Plans/Cross sections/Equipment list
	Construction Sequence Hotel	Biju	Senthil,Moncef	Crane plan, basic construction sequence	Plans,sections,Equipment list
	Planning/Scheduling	Moncef	Entire team	Construction schedule,Cashflow curve, resource histograms
ESTIMATION	RFP Processing	Estimation Manager	Participation of other team members in discussions as needed	RFP's: All Suppliers and Subcontractors	Offers
	Quantification	Estimation Manager		Quantification of all items not described above as assigned
	Tender Compilation	Estimation Manager/Technical Manager Est		Compilation of the complete commercial and technical proposals including technical writing.
COMMERCIAL	Compilation of Commercial Deviations	Neil to assign			List
	Risk Register	Nader	All Team		List